## Sheet1
Callum Bloys / 19015092			CCTP Log

Date		Tasks set			Outcomes

16/10/2021			Research VR			Gained knowledge and noted down pros and cons of VR and mitigating motion sickness

19/10/2021			Research unique puzzle mechanics and more research on how VR can be set up in Unity and unreal			Gained more undertsanding of how VR can be made and decided on a superliminal styled game

30/10/2021			Proposal document			Created a draf of my proposal document

04/11/2021			speak to supervisor about proposal and get feedback			worked on feedback from supervisor and finished off document

24/11/2021			begin setting up project on unity after deciding to use unity			progress made created unity document and installed necessry packages i.e. XR packages.

27/11/2021			Research into VR and forced perspective			researched valuable information that will be used in the research document

05/12/2021			begin reseach document			created draft of reearch document

10/12/2021			continue working on research document			worked on research questions and made a start on research methodology

12/12/2021			continue working on research document			worked on ethical and professional principles

14/12/2021			continue working on research document			worked on literature review and researched in preparation for research findings

18/12/2021			continue working on research document			made a start on research findings and more research

20/12/2021			finishing off research document			finished research document

25/12/2021			setup VR in Unity			VR is setup in unity in preparation for creating VR

27/12/2021			started working on VR			Created VR in Unity but very basic at the moment with basic movement.

03/01/2022			Working on VR			Added cubes and made it so I could pick up the cubes and drop them.

12/01/2022			adding hands to VR			Added hand that were free on oculus and added physics and collision to them.

19/01/2022			Level design			worked on creating level and environment

26/01/2022			started on forced perspective mechanic			started implementing forced perspective but had issues with scaling

04/02/2022			added objects to use forced perspective on			created objects and imported free assests from unity store to use and added XR interactble grab script.

10/02/2022			continuing level design			added a temple and trees to match the theme

23/02/2022			worked on starting room			created office room which the p;ayer will start in nd learn the controls before pressing a button to continue

02/03/2022			attempted fixing forced perspective			did not manage to fix it instead removed it to create a better one at a later date

23/03/2022			worked on new forced perspective			added new forced perspective mechanic but caused bugs so was removed.

09/04/2022			worked on VR hand animation and rigging and adding colliders			colliders and rigging was implemented on the hand succesfuly however aniation was removed

20/04/2022			bug fixing			fixed bugs

23/04/2022			texturing models			textured models that werent textured and started adding lighting

26/04/2022			adding sound			started adding a sound system however this was then left out

27/04/2022			bug fixing in prearation for hand in			fixed bugs with VR and added jumping

10/05/2022			fixed VR issue			fixed a few bug and issues with VR and fixed issue where hand would be shaking a lot

25/05/2022			working on forced perspective			added smoother pckup and moving object around.

04/06/2022			worked on puzzles and level			added more models and extra puzzle for the temple

19/06/2022			spoke to supervisor about possible better ideas for forced perspective			added new forced perspective mechanic but issues still present

27/06/2022			working on final report			working on final report

08/07/2022			continued on working on the game			started working on teleportation using teleportation provider script

15/07/2022			continued working on the final report			continued working on the final report

16/07/2022			finalising project			finalising project checking it all runs

19/07/2022			finalising final report			finalising final report